## Project Schedule V1.3
Scope | Gateway Provisioning - Project Schedule plan V1.4
| 1901-07-25 | 3/25 - 4/5 | 4/8 - 4/19 | 4/ 22- 5/3 | 5/6 - 5/17 | 5/20 -5/31 | 6/3 -6/13 | 6/10- 6/14 | 6/17 - 6/28
Modules / Integration Areas | Initiation Phase | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | GO-LIVE Phase | Hyper Care
Access credentials, Requirement Analysis, Project Schedule, Required process, Design documentation and Review | Access, Design Review & documentation | [6 empty] | CAB Approvals + GO LIVE
System Service Request Service Now - Form UI Modifications, Add new fields, Functionality Development SAP - Validate User Account in SAP, Create New USER account in SAP and Assign Roles |  | Development & Unit Testing including getting access priveleges
System Access Termination Service Now - Designing work flow for form and Integration SAP - Update New Roles for Existing USER Account, Provide Roles to SNOW for SAP USER Account |  |  | Development & Unit Testing
Notifications Service Now - Designing Notifications, Notifications Integration SAP - Provide Plant Details to SNOW for USER, Update New Plants to USER Account, Terminate User Accounts |  |  |  | Development & Unit Testing
Service Now - Complete Integration Requirements, Service Now <->Gateway <->SAP, Unit Testing & Bug fixes SAP - Unit Testing and Integration Bug fixes UAT Testing , UAT Support, Bug Fixes |  |  |  |  | Development & Unit Testing Bugs & Defect fixing |  | Project Closure |  | Project Closure
Create access requests to several users with matching or different roles. User to enter a bulk order to create access requests Upload excel template to ServiceNow to create the individual requests and trigger the approval process. | [5 empty] | Development & Unit Testing Bugs & Defect fixing |  |  | Post production support and Hyper Care
End - to - end Testing and UAT Testing
Post Go-live support and Project Closure
Business Analysis & Functional Testing
Project Management
Milestone 1
QA Testing (Browser Testing)
UAT + Regression Testing
QA Testing + QA Regression
UAT + Regression Testing
QA Testing (Browser Testing)
UAT + Regression Testing
QA Testing + Regression
UAT + Regression Testing
QA End-to-end Testing
Milestone 2
Go-Live 1
UAT + Regression Testing
QA Testing + Regression
Milestone 3
Go-Live 2
Milestone 4

## Resource Planning
572
Module / Phase |  | Reqs, Design Finalization | Access Credentials, Integration Check points, Development, Integration, QA Testing, UAT, Go Live, Hyper Care and Post Production support
|  | Requirement & Design | Sprint 1 (2 Week) |  | Sprint 2 (2 Week) |  | Sprint 3 (2 Week) |  | Sprint 4 (2 Week) |  | Sprint 5 (2 Week) |  | Sprint 6 (1 Week) | Go Live | Hyper Care (2 Week)
Resource Role | Location | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Hours
Srinivas Shada (SNOW Lead Dev) | India |  | 10 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 24 | 10 | 10 | 10 | 10 | 394
Bhanu Teja (SNOW Dev) | India |  | 10 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 10 | 12 | 12 | 444
Mashiq Navaz (SAP Dev) | India |  | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 12 | 12 | 244
Mohan Reddy (SAP Dev) | India |  | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 10 | 10 | 12 | 12 | 214
(Business Analyst / QA Testing) | India |  | 10 | 10 | 10 | 10 | 10 | 20 | 10 | 20 | 10 | 20 | 20 | 10 | 10 | 10 | 180
Sujayeendra Vallur (Project Manager) | India |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 4 | 4 | 124
Total Hours | [16 empty] | 1600

## Estimates Summary
Gateway User Provisioning Project | Effort in Hours
ServiceNow Estimates | 572
Access and authorization for Team | 60
SAP OData Services Estimates | 360
Hypercare support (2 weeks) | 120
Business Analysis and Testing Support | 180
User Bulk upload (Excel upload) - New Requirement | 184
Project Management support | 124
Total | 1600

## ServiceNow_Est.
Gateway User Provisioning ServiceNow Efforts
| Key deliverables | Effort in hours | Add. Hours for New Requirement
| 572 | 20
| Application architecture with data model design | 20
1 | System Access Request
| Modifications in the existing form | 26 | 24
| To update the Access request in ServiceNow from SAP | 20
| When access request is failed then incident should be created based on response from SAP | 26
| To get the data from SAP to ServiceNow and send the data from ServiceNow to Gateway |  | 40
| Business Rules |  | 40
| Testing/Data Validation and bug fixes | 26 | 20
| UAT and bug fixes | 26 | 20
2 | System Access Termination
| Schedule Job to match TO-DATE with Current Date in Case of User Account Termination | 26
| Process Access Termination in SAP from ServiceNow | 20
| When access termination is failed then incident should be created based on response from SAP | 26
| Testing/Data Validation and bug fixes | 20
| UAT and bug fixes | 20
3 | Notifications
| Notifications to users and managers for Access Request, Termination and Approval | 50
| Testing/Data Validation and bug fixes | 26
| UAT and bug fixes | 26
| End to End Testing/ Releases / Browser based and Responsive testing | 50
| Total Hours | 428 | 144

## SAP_OData_Services_Est.
Project # SAP GATEWAY USER PROVISIONING OData Services required from SAP to Service Now.
572
S.No. | Custom Objects (OData Services) | Details | Effort_Hours
1 | Design and Documentation | Detail Design and Documentation | 40
2 | Validate USER Account in SAP | Get Method to Validate Existing USER Account in SAP | 20
2 | Create New USER account in SAP and Assign Roles | POST method to create User account and assign roles | 60
3 | Update New Roles for Existing USER Account | PUT method to update Roles for Existing Account | 40
4 | Provide Roles to SNOW for SAP USER Account | GET Method to send all possible Roles list to SNOW | 40
5 | Provide Plant Details to SNOW for USER | GET Method tp send Plant details to SNOW | 20
6 | Update New Plants to USER Account | PUT Method to update Plants to USER Account | 20
7 | Terminate User Account | POST method to Terminate User Account | 40
8 | Unit Test for Above Objects | Unit Testing | 80
9 | UAT Support( Bug Fixes) | UAT Support | 60
|  | Total Hours | 360

## Bulk User upload Enhancement
572 | Key deliverable | Effort Hours
1 | Service Now - Development | 100
2 | SAP - Development (Design & Unit Testing support) | 20
3 | Requirement Analysis and implementation design | 24
4 | Testing | 40
| Total | 184